## Requirements
| Agencies combined requirements | [7 empty] | For Secretariat's info |  |  |  | For Builder To Fill on Submission of Scan
Admin Reference No | S/n | Description of Requirement | Acceptable Requirements | Areas | Specific Item | Quantity | Mode of Evidence | Description of Attachment | Agency | Code/Regulation | Typology | Clause | Status (Applicable , NA, Not Ready)
1 | 1 | The height of a barrier shall not be less than 1.0 m at all locations | >1000mm | All Applicable Areas | Barriers | 3 | Photo of Measurement |  | BCA | Approved Document | All | H.3.2.1(a)
2 | 2 | The barrier shall not be less than 1000mm or 850mm when measured from the last climbable toehold whichever is higher | >850mm or >1000mm | All Applicable Areas | Barriers | 3 | Photo of Measurement |  | BCA | Approved Document | All | H.3.4A.1
3 | 3 | In non-industrial buildings, the size of any opening or gap in a barrier shall not be larger than 100mm diameter sphere. | >150mm | All Applicable Areas | Barriers | 3 | Photo of Measurement |  | BCA | Approved Document | All | H.3.4.3.a
4 | 4 | In industrial buildings, the size of any opening or gap in a barrier shall not be larger than 150mm diameter sphere. | >150mm | All Applicable Areas | Barriers | 3 | Photo of Measurement |  | BCA | Approved Document | Industrial | H.3.4.3.b
5 | 5 | Gratings and gaps along the accessible route <12mm | <12mm | All Applicable Areas | Common Areas Accessible Route | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 4.1.2.1.b
6 | 6 | Width min. 1500mm (Primary Accessible Route) | >1500mm | All Applicable Areas | Common Areas Accessible Route | 3 | Photo of Measurement |  | BCA | Code of Accessibility | All | 4.2.1
7 | 7 | Width min. 1200mm (Secondary Accessible Route) | >1200mm | All Applicable Areas | Common Areas Accessible Route | 3 | Photo of Measurement |  | BCA | Code of Accessibility | All | 4.2.1.1.b
8 | 8 | Operating Controls and Devices should be located at a height of between 450 mm to 1200 mm from the floor level | 1200mm > x > 450mm | All Applicable Areas | Common Areas Accessible Route | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 6.2.2.3.b
9 | 9 | The operating part of controls, electrical sockets and switches shall be located at 350 mm or more from the internal corner of a room or obstruction as shown in Figure 64 (c). | >350mm | All Applicable Areas | Common Areas Accessible Route | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 6.2.2.5
10 | 10 | Headroom > 2.0 m (Common circulation space) | >2000mm | All Applicable Areas | Common Areas Accessible Route | 3 | Photo of Measurement |  | BCA | Approved Document | All | C.3.2.1
11 | 11 | The doorway of the entrance must be 850mm minimum for a single leaf door. If the doorway has two independently operated door leaves, at least one active leaf must be a minimum of 850mm | >850mm | All Applicable Areas | Door | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 4.4.2.1
12 | 12 | On the pull side, a minimum space of 600 mm adjacent to the leading edge of the door with a minimum clear floor space of 1500 mm wide by 1500 mm deep | >600mm | All Applicable Areas | Door | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 4.4.6.1.a
13 | 13 | On the push side, a minimum space of 300 mm adjacent to the leading edge of the door with a minimum clear floor space of 1200 mm wide by 1200 mm deep. | >300mm | All Applicable Areas | Door | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 4.4.6.1.b
14 | 14 | The leading edge of the door leaf must not be set more than 150mm from the wall surface | <150mm | All Applicable Areas | Door | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 4.4.6.3
15 | 15 | Clear Width of Ramp | >1200mm | All Applicable Areas | Ramps | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 4.6.3.1
16 | 16 | Handrails that are placed at a height of between 800 mm and 900 mm above the floor level; and | >900mm x > 800mm | All Applicable Areas | Ramps | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 4.6.6.1.c
17 | 17 | Where service counters are provided, part of the counter shall not be more than 800 mm from the floor | <800mm | All Applicable Areas | Service and Information Counter | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 6.4.1
18 | 18 | An accessible gate with a width of 850 mm or more shall be provided beside a turnstile as shown in Figure 16. | >850mm | All Applicable Areas | Turnstile | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 4.2.2.1
19 | 19 | Areas with mode of ventilation indicated as AC or MV shall comply with SS 553. For AC systems, QP to confirm fresh air is provided to the system for ventilation of the room/space. | - | All Applicable Areas | Ventilation System | 1 for each type of system | Photo of Additional Evidence | To show picture of the MV outlet if it could not be seen from the Scan | BCA | Approved Document | All | G.3.1
20 | 20 | Headroom > 2.2m | >2200mm | Carpark | Common Parking Lots and Driveway | 3 | Photo of Measurement |  | BCA | Approved Document | All | C.3.2.2
21 | 21 | Safety barrier >1m | >1000mm | Carpark | Common Parking Lots and Driveway | 3 | Photo of Measurement |  | BCA | Approved Document | All | H.3.2.1(a)
22 | 22 | The lift landing call button shall be located at least 350 mm away from a wall or obstruction | >350 mm | Lift | Lift Lobby for Accessiblity | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 4.9.4.1(c)
23 | 23 | A momentary audible announcement must be provided to signal each call registered and the storey reached. | - | Lift | Lift Lobby for Accessiblity | 1 | Video Recording | To show for 1 accessible lift and the duration to be sufficient to hear the annoucements | BCA | Code of Accessibility | All | 4.8.2.6
24 | 24 | Barrier's size of opening <500mm | <500mm | Maintenance Areas | Maintenance Areas | 3 | Photo of Measurement |  | BCA | Approved Document | All | H.3.4.4A
25 | 25 | The width of the access route leading to the bathroom, or the room where the bathroom is, shall be a minimum of 1000 mm, subject to the provisions in Table 6. | >1000mm | Residential Unit | Accessible Route | 1 | Photo of Measurement |  | BCA | Code of Accessibility | Residential | 7.3.3
26 | 26 | Difference in level between floor of the entrance to the residential unit and the abutting common area shall not be more than 50mm | <50mm | Residential Unit | Door | 1 | Photo of Measurement |  | BCA | Code of Accessibility | Residential | 7.2.3
27 | 27 | The doorway of the bathroom for future retrofitting and the clear space in front of the doorway shall comply with the dimensions in Table 6 | - | Residential Unit | Retrofit Bathroom | 1 | Photo of Measurement |  | BCA | Code of Accessibility | Residential | 7.3.4
28 | 28 | The bathroom for future retrofitting shall have a clear floor space of at least 1000 mm by 1000 mm at the front edge of the water closet. In addition, the WC shall be positioned by not less than 450mm from the wall. | >1000 by 1000 >450mm | Residential Unit | Retrofit Bathroom | 1 | Photo of Measurement |  | BCA | Code of Accessibility | Residential | 7.3.5
29 | 29 | There shall preferably be no change in level of the floor surface at the doorway of the bathroom. If there is a change in level, it shall not be more than 25 mm. | <25mm | Residential Unit | Retrofit Bathroom | 1 | Photo of Measurement |  | BCA | Code of Accessibility | Residential | 7.3.6
30 | 30 | A staircase shall have barriers against falling from 1.0m or more from an open side | >1000mm | Staircase Area | Barriers | 1 | Photo of Measurement |  | BCA | Approved Document | All | E.2.2.e
31 | 31 | The minimum clear width of staircase shall not be less than 1000mm. | >1000mm | Staircase Area | Staircase | 1 | Photo of Measurement |  | BCA | Approved Document | All | E.3.3.1
32 | 32 | The height of riser shall not be more than 175mm. | <175mm | Staircase Area | Staircase | 3 | Photo of Measurement |  | BCA | Approved Document | All | E.3.4.1
33 | 33 | Handrail height between 800mm and 1000mm | 1000mm > x > 800mm | Staircase Area | Staircase | 1 | Photo of Measurement |  | BCA | Approved Document | All | E.3.6.2
34 | 34 | Gap between handrail and wall, (>40mm for smooth finish, >60mm for rough finish) | >40mm (or >60mm) | Staircase Area | Staircase | 1 | Photo of Measurement |  | BCA | Approved Document | All | E.3.6.3
35 | 35 | The width of a tread of a staircase shall not be less than 225mm/250mm/275mm. | >225/250/275mm | Staircase Area | Staircase | 3 | Photo of Measurement |  | BCA | Approved Document | All | E.3.4.2
36 | 36 | Have minimum clear dimensions between opposite walls of 1750mm or more | >1750mm | Toilet area | Accessible Individual Washroom | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 5.2.1(a)
37 | 37 | have a minimum clear floor space of 750 mm wide by 1200 mm deep from grab bars location and without steps in front of the urinals; and | >750mm by 1200mm | Toilet area | Ambulant Urinal | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 5.5.1.b
38 | 38 | grab bar inside the ambulant toilet shall be at least 600 mm long on the inside of an out-swinging door; | >600mm | Toilet area | Door | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 5.6.1.1.c.i
39 | 39 | grab bar located so that it is 130 mm or less from the hinged-side of the door; and | >130mm | Toilet area | Door | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 5.6.1.1.c.ii
40 | 40 | be located between 460 mm to 480 mm from the centre line of the water closet to the adjacent wall and have a clear dimension of 750 mm from the front edge of the water closet to the rear wall to facilitate side transfer; | 480mm > x > 460mm | Toilet area | Water Closet | 1 | Photo of Measurement |  | BCA | Code of Accessibility | All | 5.6.6.1.a
272 | 41 | Clearance of 2.0 m or more at the front of chiller unit piping section for tube maintenance and cleaning, repair and replacement of bigger components | ≥2000mm | Chiller plant area | Chillers | 1 | Photo of Measurement |  | BCA | Code for Environmental Sustainability of Buildings, 4th edition | All
273 | 42 | Clearance of 1.2 m or more between the chillers measured from plinth to plinth for regular maintenance | ≥1200mm | Chiller plant area | Chillers | 1 | Photo of Measurement | Both sides of one of the chillers | BCA | Code for Environmental Sustainability of Buildings, 4th edition | All
274 | 43 | Clearance of 1.5 m or more above the chiller to facilitate maintenance, overhaul or replacement | ≥1500mm | Chiller plant area | Chillers | 1 | Photo of Measurement |  | BCA | Code for Environmental Sustainability of Buildings, 4th edition | All
275 | 44 | Except for the areas where the pipes are connected, clearance of 0.6 m or more is to be provided around the pump for regular maintenance | ≥600mm | Chiller plant and condenser area | Chilled water pumps and condensers water pumps | 1 | Photo of Measurement | Front, back and sides of one of the chilled water and condenser water pumps | BCA | Code for Environmental Sustainability of Buildings, 4th edition | All
276 | 45 | Clear headroom of 1.0 m or more above the pump and motor to facilitate maintenance, overhaul or replacement. | ≥1000mm | Chiller plant and condenser area | Chilled water pumps and condensers water pumps | 1 | Photo of Measurement |  | BCA | Code for Environmental Sustainability of Buildings, 4th edition | All
277 | 46 | Provision of maintenance platform, stairs and catwalks of 600 mm width or more with handrails around the cooling towers and access to the level for periodic maintenance and inspection of the water basin and fill media | ≥600mm | Cooling towers | Cooling towers | 1 | Photo of i) Overall view of cooling tower showing maintenance platform at fill media / louvres, ii) Measurement of maintenance platform width, iii) Handrails, iv) Access to cooling tower door, and v) Access to platform via staircase or cat ladder |  | BCA | Code for Environmental Sustainability of Buildings, 4th edition | All
278 | 47 | Clear distance of 2.0 m or more from the top of cooling towers to the location of the trellis, where applicable | ≥2000mm | Cooling towers | Cooling towers | 1 | Photo of Measurement |  | BCA | Code for Environmental Sustainability of Buildings, 4th edition | All
279 | 48 | Air handling units (AHUs) of cooling capacity greater than 35 kW shall be floor mounted as stipulated in SS 553 | - | AHU area | AHU | All AHUs | Photo of AHU positioning (mounting type) and access to the AHU. |  | BCA | Code for Environmental Sustainability of Buildings, 4th edition | All
280 | 49 | Provide minimum 1.0 m clearance from the AHU room door entrance to the AHU for general maintenance | ≥1000mm | AHU area | AHU | 1 | Photo of Measurement |  | BCA | Code for Environmental Sustainability of Buildings, 4th edition | All
281 | 50 | Provide minimum 800mm clearance after pipe connection to facilitate cooling coil cleaning and filter access | ≥800mm | AHU area | AHU | 1 | Photo of Measurement |  | BCA | Code for Environmental Sustainability of Buildings, 4th edition | All
282 | 51 | Provide minimum 800 mm clearance for fan/motor access and maintenance (if the access is not from the cooling coil connection side) | ≥800mm | AHU area | AHU | 1 | Photo of Measurement |  | BCA | Code for Environmental Sustainability of Buildings, 4th edition | All
283 | 52 | Provide minimum 600 mm clear width for general access and maintenance | ≥600mm | AHU area | AHU | 1 | Photo of Measurement | Photo of clearance for sides of one of the AHUs other than those sides that comply with S/N 51 and 52. | BCA | Code for Environmental Sustainability of Buildings, 4th edition | All
41 | 53 | Please measure the MDF room a) Length b) Width c) Height d) Height of the door kerb | Per code requirements | Main Distribution Frame (MDF) room | MDF room | All MDF | Photo of Measurement | While the room is usually rect/square, for odd shape need to measure the perimieter. Please also attahced the picture of the proposed locations and dimensions of the 1) the 3 electrical DB board 2) the earth bar | IMDA | CODE OF PRACTICE FOR INFO-COMMUNICATION FACILITIES IN BUILDINGS | All | -
42 | 54 | Please measure the Size and Height of cable ladder in the MDF | Per code requirements | Main Distribution Frame (MDF) room | MDF room | 1 | Photo of Measurement | Please measure the height and provide a sample measurement around the room | IMDA | CODE OF PRACTICE FOR INFO-COMMUNICATION FACILITIES IN BUILDINGS | All
43 | 55 | Please show number of lead-in pipes into MDF room(s) | Per code requirements | Main Distribution Frame (MDF) room | MDF room | All MDF | Photo of Additional Evidence | To provude the close up photo of top view, both side views and the front view | IMDA | CODE OF PRACTICE FOR INFO-COMMUNICATION FACILITIES IN BUILDINGS | All | -
44 | 56 | Please measure the TER room a) Length b) Width c) Height d) Height of the door kerb | Per code requirements | Telecommunication Equipment Room (TER) | TER Rooms | All TER | Photo of Measurement | While the room is usually rect/square, for odd shape need to measure the perimieter. Please also attahced the picture of the proposed locations and dimensions of the 2 electrical DB board. | IMDA | CODE OF PRACTICE FOR INFO-COMMUNICATION FACILITIES IN BUILDINGS | All | -
45 | 57 | Please measure the Size and Height of cable ladder in the TER | Per code requirements | Telecommunication Equipment Room (TER) | TER Rooms | 1 | Photo of Measurement | Please measure the height and provide a sample measurement around the room | IMDA | CODE OF PRACTICE FOR INFO-COMMUNICATION FACILITIES IN BUILDINGS | All
46 | 58 | Please show number of lead-in pipes into TER(s) | Per code requirements | Telecommunication Equipment Room (TER) | TER Rooms | All TER | Photo of Additional Evidence | To provude the close up photo of top view, both side views and the front view | IMDA | CODE OF PRACTICE FOR INFO-COMMUNICATION FACILITIES IN BUILDINGS | All | -
47 | 59 | Please measure size of cabletray (a) between MDF room to each Riser | Per code requirements | All Applicable Areas | MDF room | All | Photo of Measurement | Please take a picture from inside and from the outside. To measure the hieght of the tray from the floor to the tray | IMDA | CODE OF PRACTICE FOR INFO-COMMUNICATION FACILITIES IN BUILDINGS | All | -
48 | 60 | Please measure size of cabletray (c) between lead-in and underground pipes, terminating into a basement (installed with Mass Cable Transit), to the MDF room. | Per code requirements | All Applicable Areas | MDF room | All | Photo of Measurement | Please provide the photo of the MCT (measure the dimaeter of 1 sample, ensure RGP150) Please measure the gap between Tray and MCT 600 Please measure the clearance (at the Highest and lowest points along the common tray) - from the floor to the cable tray and - from the tray to the service | IMDA | CODE OF PRACTICE FOR INFO-COMMUNICATION FACILITIES IN BUILDINGS | All | -
49 | 61 | Please measure the compartment size a) Length and Width and Height (internal dimentions) b) the Width of cable trays or trunking c) kerb of the door | Per code requirements | All Applicable Areas | Telecommunication riser | 1 | Photo of Measurement | For HDB, please provide photo of the openings behind the trunking Sample 1 unit if all the units are of typical dimension, if not typical, please take each variation once) In addition, when there is a turning, please also to take it at that level. | IMDA | CODE OF PRACTICE FOR INFO-COMMUNICATION FACILITIES IN BUILDINGS | All | -
50 | 62 | Please measure size of cabletray (b) between TER to each Riser | Per code requirements | All Applicable Areas | TER | All | Photo of Measurement | Please take a picture from inside and from the outside. To measure the hieght of the tray from the floor to the tray | IMDA | CODE OF PRACTICE FOR INFO-COMMUNICATION FACILITIES IN BUILDINGS | All | -
51 | 63 | Please provide the quantity of the pipes and declare the size of manhole | Per code requirements | All Applicable Areas | Underground pipes (between manholes) | All | Photo of Additional Evidence | Please show the picture of the manhole , the length and width and all 4 sides OR provide a 360 capture spot capture within the manhole | IMDA | CODE OF PRACTICE FOR INFO-COMMUNICATION FACILITIES IN BUILDINGS | All | -
52 | 64 | Please provide the lead in pipes details (outside of the development) | Per code requirements | All Applicable Areas |  |  |  | show the photo of the exposed pipe with the depth of the pipe | IMDA | CODE OF PRACTICE FOR INFO-COMMUNICATION FACILITIES IN BUILDINGS | All
53 | 65 | Please provide the 2 way Air-blown Fibre Micro ducts from Telcom riser to each unit | Per code requirements | All Applicable Areas |  |  |  | Show the photo of the Tube Patch Panel in the riser Show the photo of the 2 way Air blown fibre micro duct with the slack | IMDA |  | Non-residential buildings
54 | 66 | Parking Provision - no. of car, motorcycle, bicycle, lorry/loading & loading and coach lots provided and temporary loading/unloading area for movers/heavy vehicles in residential developments. | As per approved Building Plans | All parking place | Parking lots | All | Photo | Developments Vehicle Parking | LTA | Code of Practice for Vehicle Parking Provision in Development Proposals | All except developments listed in Appendix D of COP on Vehicle Parking Provision in Development Proposals, HDB public housing and Government owned buildings. | 1.3 1.4 1.5 1.6
55 | 67 | Parking Layout - includes parking geometry, traffic circulation, blind-spot areas, cyclists' route & wayfinding signage. | As per approved Building Plans | All parking place | Parking lot size, width of ramps, width of accessways, width of parking aisles, turning radius, ramp gradients and headroom clearance. | All | Photo Measurement | Developments Vehicle Parking | LTA | Code of Practice for Vehicle Parking Provision in Development Proposals | All except developments listed in Appendix D of COP on Vehicle Parking Provision in Development Proposals, HDB public housing and Government owned buildings. | 2.1.1 2.1.2 2.1.3 2.1.4 2.1.5 2.2.1 2.3 2.4
56 | 68 | Adequate Information for Motorists | - | All parking place | Signages, road/arrow markings, height clearance bar, convex mirror, etc. | All | Photo | Developments Vehicle Parking | LTA | Code of Practice for Vehicle Parking Provision in Development Proposals | All except developments listed in Appendix D of COP on Vehicle Parking Provision in Development Proposals, HDB public housing and Government owned buildings. | 4.8 4.9
57 | 69 | Mechanised Parking/Car Lifts System | As per approved Building Plans | All parking place | System fully operational, compliance on parking platform/lift dimensions, headroom clearance, holding bays, queuing spaces, signages on limitations & instruction on use of system. | All | Photo Measurement & video | Developments Vehicle Parking | LTA | Code of Practice for Vehicle Parking Provision in Development Proposals | All except developments listed in Appendix D of COP on Vehicle Parking Provision in Development Proposals, HDB public housing and Government owned buildings. | 3.2.1 3.2.2 3.3.1 3.3.2 3.3.3
58 | 70 | Movement joint should be of good condition and joint gap should be within allowable range | As per LTA's design requirement | All | Movement joint | All | Photo of Measurement / video / Photo of Additional Evidence | Public Streets Road Culvert | LTA | Civil Design Criteria Material & Workmanship Specification |  | 15.3
59 | 71 | All cracks on concrete surfaces should be <0.4mm | <0.4mm | All | - | All | Photo of Measurement | Public Streets Road Culvert | LTA | Material & Workmanship Specification |  | 11.16.1
62 | 74 | Location of access points | - | All | - | All | Photo of Additional Evidence / video | Public Streets Road Culvert | LTA | Material & Workmanship Specification |  | 1.3.1.2(d)
64 | 76 | All cracks on concrete surfaces should be <0.4mm | <0.4mm | All | - | All | Photo of Measurement / video | Retaining Wall | LTA | Material & Workmanship Specification |  | 11.16.1
65 | 77 | Welding points free of corrosion/damages | No corrosion/ damages | All welding points | Welding | All | Photo of Additional Evidence | Directional/Height Limit Gantry | LTA | Material & Workmanship Specification |  | 12.6
66 | 78 | Signs date sticker | Signs | All | Signs | All | Photo of Additional Evidence | Directional/Height Limit Gantry | LTA | Material & Workmanship Specification |  | 10.11
67 | 79 | height of gantry | NA | All | - | All | Photo of Additional Evidence | Directional/Height Limit Gantry | LTA | Civil Design Criteria Material & Workmanship Specification |  | 10.7
68 | 80 | Bridge movement joint should be of good condition and joint gap should be within Allowable range | As per LTA's design requirement | All | Movement joint | All | Photo of Measurement / video / Photo of Additional Evidence | Flyover/Viaduct/Vehicular Bridge | LTA | Civil Design Criteria Material & Workmanship Specification |  | 15.3
69 | 81 | Bridge movement joint waterproofing done properly | no leakage | All | Movement joint | All | Video | Flyover/Viaduct/Vehicular Bridge | LTA | Civil Design Criteria Material & Workmanship Specification |  | 15.3.8
70 | 82 | Bridge movement joint end treatment done properly | As per LTA's design requirement | All | Movement joint | All | Photo of Additional Evidence /Video | Flyover/Viaduct/Vehicular Bridge | LTA | Civil Design Criteria Material & Workmanship Specification |  | 15.3.5
72 | 84 | Bridge bearings movement should be within Allowable limits and of good condition (free of corrosion/defects) | no corrosion/defects | All | Bearings | All | Photo of Measurement /Video | Flyover/Viaduct/Vehicular Bridge | LTA | Civil Design Criteria Material & Workmanship Specification |  | 15.2
75 | 87 | All cracks on concrete surfaces should be <0.4mm | <0.4mm | All | - | All | Photo of Measurement | Flyover/Viaduct/Vehicular Bridge | LTA | Material & Workmanship Specification |  | 11.16.1
76 | 88 | Signs - Name signs, 4.5m height limit signs to be free of peeling/fading and properly secured, capture dating sticker | no defects | All | Signs | All | Photo of Additional Evidence /Video | Flyover/Viaduct/Vehicular Bridge | LTA | Material & Workmanship Specification |  | 10.8
77 | 89 | Height of parapet and P1-2rail | As per SDRE | All | P1-2 rail parapet system | All | Photo of Additional Evidence /Video | Flyover/Viaduct/Vehicular Bridge | LTA | Civil Design Criteria Standard Details of Road Elements |  | 9.9
78 | 90 | Grating is placed in the correct direction | As per SDRE | All | Grating | All | Photo of Additional Evidence /Video | Flyover/Viaduct/Vehicular Bridge | LTA | COP on Surface Water Drainage |  | 9.11
79 | 91 | Bridge movement joint should be of good condition and joint gap should be within Allowable range | As per LTA's design requirement | All | Movement joint | All | Photo of Measurement | Vehicular Underpass | LTA | Civil Design Criteria Material & Workmanship Specification |  | 15.3
80 | 92 | All cracks on concrete surfaces (VUP + Storage Chambers (if any) + Substation (if any)) should be <0.4mm | <0.4mm | All | - | All | Photo of Measurement | Vehicular Underpass | LTA | Material & Workmanship Specification |  | 11.16.1
81 | 93 | Signs - Name signs, 4.5m height limit signs to be free of peeling/fading and properly secured, capture dating sticker | no defects | All | Signs | All | Photo of Additional Evidence | Vehicular Underpass | LTA | Material & Workmanship Specification |  | 10.8
85 | 97 | Location of access points | - | All | Access point | All | Photo of Additional Evidence | Vehicular Underpass | LTA | Material & Workmanship Specification |  | 1.3.1.2(d)
86 | 98 | Grating is placed in the correct direction | As per SDRE | All | Grating | All | Photo of Additional Evidence /Video | Vehicular Underpass | LTA | COP on Surface Water Drainage |  | 9.11
87 | 99 | Kerb height from road | As per SDRE | All | Kerb | 1 | Photo of Measurement | Road Related facilities | LTA | Standard Details of Road Elements |  | LTA/SDRE14/3/KER1
88 | 100 | Sign dating sticker | As per SDRE | All | Sign | 1 | Photo of Measurement | Road Related facilities | LTA | Standard Details of Road Elements
89 | 101 | VIG height from road | As per SDRE | All | VIG | 1 | Photo of Measurement | Road Related facilities | LTA | Standard Details of Road Elements |  | LTA/SDRE14/6/VIG4
90 | 102 | Railing height | As per SDRE | All | Railing | 1 | Photo of Measurement | Road Related facilities | LTA | Standard Details of Road Elements |  | LTA/SDRE14/5/RAL1
91 | 103 | Bollard setback | As per SDRE | All | Bollard | 1 | Photo of Measurement | Road Related facilities | LTA | Standard Details of Road Elements |  | LTA/SDRE14/14/BOL1 LTA/SDRE14/14/BOL3 LTA/SDRE14/14/BOL4 LTA/SDRE14/14/BOL5
92 | 104 | Covered linkway columns | >2.4m height Paint Treatment as per M&W | Covered linkway | Column | All | Photo Measurement | Covered linkway (CLW) | LTA | Infrastructure Design Criteria Material & Workmanship Specification |  | IDC Vol C Check list 1 ,4 & 7 and IDC Vol C 1.4. M & W 12.8.4 Paints
93 | 105 | Covered linkway beams | Paint Treatment as per M&W | Covered linkway | Beams | All | Photo | Covered linkway (CLW) | LTA | Material & Workmanship Specification |  | IDC Vol C Check list 1 ,4 & 7 and IDC Vol C 1.4.
94 | 106 | Covered linkway interfacing details to adjacent structures | Flashing and sealant as per M&W | Covered linkway | Interfacing details | All | Photo | Covered linkway (CLW) | LTA | Infrastructure Design Criteria Material & Workmanship Specification |  | IDC Vol C Check list 1 ,4 & 7 and IDC Vol C 1.4.
95 | 107 | POB deck | Gradient crossfAll for water run-off | POB | Floor/Deck | All | Photo Measurement | Pedestrian Overhead Bridge (POB) | LTA | Infrastructure Design Criteria |  | IDC Vol C Annex Refer to POB/PUP. Chk list 5 and 6
96 | 108 | POB roof columns | >2.4m height Paint Treatment as per M&W | POB | Column | All | Photo Measurement | Pedestrian Overhead Bridge (POB) | LTA | Infrastructure Design Criteria Material & Workmanship Specification
97 | 109 | POB roof beams | Paint Treatment as per M&W | POB | Beams | All | Photo | Pedestrian Overhead Bridge (POB) | LTA | Material & Workmanship Specification |  | IDC Vol C Annex Refer to POB/PUP. Chk list 5 and 6
98 | 110 | POB staircase thread, riser, tactile and nosing tile | Thread: 300mm Riser: 150mm Tactile and nosing tile to follow SDRE and IDC guideline | POB | Thread Riser Tactile tile Nosing tile | All | Photo Measurement | Pedestrian Overhead Bridge (POB) | LTA | Infrastructure Design Criteria Standard Details of Road Elements Code of Accessibility |  | IDC Vol C Annex Refer to POB/PUP. Chk list 5 and 6
99 | 111 | POB railing | >1.1m | POB | Railing | All | Photo Measurement | Pedestrian Overhead Bridge (POB) | LTA | Infrastructure Design Criteria |  | IDC Vol C Annex Refer to POB/PUP. Chk list 5 and 6
100 | 112 | Rain water down pipe, cleaning eye | Provision of cleaning eye and proper discharge | POB | RWDP | All | Photo | Pedestrian Overhead Bridge (POB) | LTA | Infrastructure Design Criteria |  | IDC Vol C Annex Refer to POB/PUP. Chk list 5 and 6
101 | 113 | POB interfacing details to adjacent structures | Flashing and sealant as per M&W | POB | Interfacing details | All | Photo | Pedestrian Overhead Bridge (POB) | LTA | Infrastructure Design Criteria Material & Workmanship Specification |  | IDC Vol C Annex Refer to POB/PUP. Chk list 5 and 6
102 | 114 | POB Lift shaft waterproofing | No waterponding/seepage spots | POB | Lift shaft | All | Photos | Pedestrian Overhead Bridge (POB) | LTA | Infrastructure Design Criteria Material & Workmanship Specification |  | IDC Vol C Annex Refer to POB/PUP. Chk list 5 and 6
103 | 115 | PUP floor | Gradient crossfAll for water run-off | PUP | Gradient | All | Photo Measurement | Pedestrian Underpass (PUP) | LTA | Infrastructure Design Criteria |  | IDC Vol C Annex Refer to PUP Cpt 1. Chk list 5 and 6
104 | 116 | PUP wAll | No tile or concrete cracks or water seepage Provision of access points for cladded wAll | PUP | Tile Concrete finishing Cladding | All | Photo | Pedestrian Underpass (PUP) | LTA | Infrastructure Design Criteria Material & Workmanship Specification |  | IDC Vol C Annex Refer to PUP Cpt 1. Chk list 5 and 6
105 | 117 | PUP ceiling | No cracks or water seepage Provision of access points for false ceiling | PUP | Concrete finishing False ceiling | All | Photo | Pedestrian Underpass (PUP) | LTA | Infrastructure Design Criteria Material & Workmanship Specification |  | IDC Vol C Annex Refer to PUP Cpt 1. Chk list 5 and 6
106 | 118 | PUP gratings | 750x850mm 850x1000mm 1500x1500mm | PUP | Grating | All | Photo Measurement | Pedestrian Underpass (PUP) | LTA | Standard Details of Road Elements |  | IDC Vol C Annex Refer to PUP Cpt 1. Chk list 5 and 6
107 | 119 | PUP ramps entrance | Gradient crossfAll for water run-off | PUP | Gradient | All | Photo Measurement | Pedestrian Underpass (PUP) | LTA | Infrastructure Design Criteria Material & Workmanship Specification |  | IDC Vol C Annex Refer to PUP Cpt 1. Chk list 5 and 6
108 | 120 | PUP staircase thread, riser, tactile and nosing tile | Thread: 300mm Riser: 150mm Tactile and nosing tile to follow SDRE and IDC guideline | PUP | Thread Riser Tactile tile Nosing tile | All | Photo Measurement | Pedestrian Underpass (PUP) | LTA | Infrastructure Design Criteria Standard Details of Road Elements Code of Accessibility |  | IDC Vol C Annex Refer to PUP Cpt 1. Chk list 5 and 6
109 | 121 | PUP railing | >1.1m | PUP | Railing height | All | Photo Measurement | Pedestrian Underpass (PUP) | LTA | Infrastructure Design Criteria |  | IDC Vol C Annex Refer to PUP Cpt 1. Chk list 5 and 6
110 | 122 | PUP interfacing details to adjacent structures | Flashing and sealant as per M&W | PUP | Interfacing details | All | Photo | Pedestrian Underpass (PUP) | LTA | Infrastructure Design Criteria Material & Workmanship Specification |  | IDC Vol C Annex Refer to PUP Cpt 1. Chk list 5 and 6
111 | 123 | Footbridge deck | Gradient crossfAll for water run-off | FB | Floor/Deck | All | Photo Measurement | Footbridge (FB) | LTA | Infrastructure Design Criteria |  | IDC Vol C Annex Refer to POB/PUP. Chk list 5 and 6
112 | 124 | Footbridge roof columns | 1. >2.4m height 2. Paint treatment as per M&W | FB | Column | All | Photo Measurement | Footbridge (FB) | LTA | Infrastructure Design Criteria Material & Workmanship Specification |  | IDC Vol C Annex Refer to POB/PUP. Chk list 5 and 6 M & W 12.8.4 Paints
113 | 125 | Footbridge roof beams | Paint Treatment as per M&W | FB | Beams | All | Photo | Footbridge (FB) | LTA | Material & Workmanship Specification |  | M& W Spec1 2.8.4
114 | 126 | Footbridge railing | >1.1m | FB | Railing | All | Photo Measurement | Footbridge (FB) | LTA | Infrastructure Design Criteria |  | IDC Vol C Annex Refer to POB/PUP. Chk list 5 and 6
115 | 127 | Footbridge staircase thread, riser, tactile and nosing tile | Thread: 300mm Riser: 150mm Tactile and nosing tile to follow SDRE and IDC guideline | FB | Thread Riser Tactile tile Nosing tile | All | Photo Measurement | Footbridge (FB) | LTA | Infrastructure Design Criteria Standard Details of Road Elements Code of Accessibility |  | IDC Vol C Annex Refer to POB/PUP. Chk list 5 and 6
116 | 128 | PUDO platform | Gradient crossfAll for water run-off | PUDO | Floor/Deck | All | Photo Measurement | Pick Up Drop Off Shelter (PUDO) | LTA | Infrastructure Design Criteria |  | IDC Vol C Annex Chpt 1 and annex A3 and A4
117 | 129 | PUDO columns | 1. >2.4m height 2. Paint treatment as per M&W | PUDO | Column | All | Photo Measurement | Pick Up Drop Off Shelter (PUDO) | LTA | Infrastructure Design Criteria Material & Workmanship Specification |  | IDC Vol C Annex Chpt 1 and annex A3 and A4. M & W 12.8.4 Paints
118 | 130 | PUDO beams | Paint Treatment as per M&W | PUDO | Beams | All | Photo | Pick Up Drop Off Shelter (PUDO) | LTA | Material & Workmanship Specification |  | IDC Vol C Annex Chpt 1 and annex A3 and A4
119 | 131 | PUDO bollards | 1m height Provision of reflective band | PUDO | Bollards | All | Photo Measurement | Pick Up Drop Off Shelter (PUDO) | LTA | Standard Details of Road Elements |  | IDC Vol C Annex Chpt 1 and annex A3 and A4
120 | 132 | PUDO catch basins | Punch through the keyhole | PUDO | Catch Basin | All | Photo | Pick Up Drop Off Shelter (PUDO) | LTA | Standard Details of Road Elements |  | IDC Vol C Annex Chpt 1 and annex A3 and A4
121 | 133 | PUDO seats | Height >450mm | PUDO | Seats | All | Photo Measurement | Pick Up Drop Off Shelter (PUDO) | LTA | Infrastructure Design Criteria Standard Details of Road Elements |  | IDC Vol C Annex Chpt 1 and annex A3 and A4
122 | 134 | PUDO interfacing details to adjacent structures | Flashing and sealant as per M&W | PUDO | Interfacing details | All | Photo | Pick Up Drop Off Shelter (PUDO) | LTA | Infrastructure Design Criteria Material & Workmanship Specification |  | IDC Vol C Annex Chpt 1 and annex A3 and A4
123 | 135 | Bus shelter platform | Gradient crossfAll for water run-off | BS | Floor/Deck | All | Photo Measurement | Bus Shelter (BS) | LTA | Infrastructure Design Criteria |  | SDRE Chpt 11, IDC Vol C Check list 1 and 2 and IDC Vol C Annex A5 to 12
124 | 136 | Bus shelter columns | >2.4m height Paint treatment as per M&W | BS | Column | All | Photo Measurement | Bus Shelter (BS) | LTA | Infrastructure Design Criteria Material & Workmanship Specification |  | SDRE Chpt 11, IDC Vol C Check list 1 and 2 and IDC Vol C Annex A5 to 12. M & W 12.8.4 Paints
125 | 137 | Bus shelter beams | Paint Treatment as per M&W | BS | Beams | All | Photo | Bus Shelter (BS) | LTA | Material & Workmanship Specification |  | SDRE Chpt 11, IDC Vol C Check list 1 and 2 and IDC Vol C Annex A5 to 12
126 | 138 | Bus information pole | >2.4m height | BS | Information pole | All | Photo Measurement | Bus Shelter (BS) | LTA | Infrastructure Design Criteria |  | SDRE Chpt 11, IDC Vol C Check list 1 and 2 and IDC Vol C Annex A5 to 12
127 | 139 | Bus shelter bollards | 1m height Provision of reflective band | BS | Bollards | All | Photo Measurement | Bus Shelter (BS) | LTA | Standard Details of Road Elements |  | SDRE Chpt 11, IDC Vol C Check list 1 and 2 and IDC Vol C Annex A5 to 12
128 | 140 | Bus shelter catch basins | Punch through the keyhole | BS | Catch Basin | All | Photo | Bus Shelter (BS) | LTA | Standard Details of Road Elements |  | LTA/SDRE14/11/BUS3
129 | 141 | Bus shelter seats | Height >450mm | BS | Seats | All | Photo Measurement | Bus Shelter (BS) | LTA | Infrastructure Design Criteria |  | SDRE Chpt 11, IDC Vol C Check list 1 and 2 and IDC Vol C Annex A5 to 12
130 | 142 | Bus shelter interfacing details with adjacent structures (open channel/flashing) | Flashing and sealant as per M&W | BS | Interfacing details | All | Photo | Bus Shelter (BS) | LTA | Infrastructure Design Criteria Material & Workmanship Specification |  | SDRE Chpt 11, IDC Vol C Check list 1 and 2 and IDC Vol C Annex A5 to 12
131 | 143 | Taxi shelter platform | Gradient crossfAll for water run-off | TS | Floor/Deck | All | Photo Measurement | Taxi Shelter (TS) | LTA | Infrastructure Design Criteria |  | IDC Vol C Annex Chpt 1 and annex A3 and A4
132 | 144 | Taxi shelter columns | >2.4m height Paint treatment as per M&W | TS | Column | All | Photo Measurement | Taxi Shelter (TS) | LTA | Infrastructure Design Criteria Material & Workmanship Specification |  | IDC Vol C Annex Chpt 1 and annex A3 and A4. M & W 12.8.4 Paints
133 | 145 | Taxi information pole | >2.4m height | TS | Information pole | All | Photo Measurement | Taxi Shelter (TS) | LTA | Infrastructure Design Criteria |  | IDC Vol C Annex Chpt 1 and annex A3 and A4
134 | 146 | Taxi shelter bollards | 1m height Provision of reflective band | TS | Bollards | All | Photo Measurement | Taxi Shelter (TS) | LTA | Standard Details of Road Elements |  | IDC Vol C Annex Chpt 1 and annex A3 and A4
135 | 147 | Taxi shelter catch basins | Punch through the keyhole | TS | Catch Basin | All | Photo | Taxi Shelter (TS) | LTA | Standard Details of Road Elements |  | IDC Vol C Annex Chpt 1 and annex A3 and A4
136 | 148 | Taxi shelter interfacing details with adjacent structures (open channel/flashing) | Flashing and sealant as per M&W | TS | Interfacing details | All | Photo | Taxi Shelter (TS) | LTA | Infrastructure Design Criteria Material & Workmanship Specification |  | IDC Vol C Annex Chpt 1 and annex A3 and A4
264 | 149 | Height of Pedestrian Railing | IDC / AMG requirement | All | Footpath / Cycling Path | All | Photo of Measurement | Flyover/Viaduct/Vehicular Bridge | LTA | Infrastructure Design Criteria (IDC) | All | 2.10.2
137 | 150 | Width of the footpath must be at least 1.8m according to current standards | 1.8m | All footpaths within public street | Footpath | All | Photo Measurement | Footpath | LTA | Standard Details of Road Elements |  | LTA/SDRE14/3/KER5
138 | 151 | Tactile tiles should have a clearance of minimum 300mm from road kerb edge | 300mm | All footpaths within public street | Footpath (Tactile tiles) | All | Photo Measurement | Footpath | LTA | Standard Details of Road Elements |  | LTA/SDRE14/3/KER5
140 | 153 | Gradient of ramp must not be steeper than 1:12 | 1:12 | All footpaths within public street | Footpath | All | Photo Measurement | Footpath | LTA | Standard Details of Road Elements |  | LTA/SDRE14/3/KER5
141 | 154 | Ramp at crossing must have gradient not steeper than 1:40 | 1:40 | All footpaths within public street | Footpath | All | Photo Measurement | Footpath | LTA | Standard Details of Road Elements |  | LTA/SDRE14/3/KER5
142 | 155 | Footpath cross fall gradient is to be at 1:40, with minimum 45mm cover and wire brushed finishing | 1:40 and min 45mm | All footpaths within public street | Footpath | All | Photo Measurement | Footpath | LTA | Standard Details of Road Elements |  | LTA/SDRE14/3/KER5
143 | 156 | Gratings on the footpath must be in either of the two sizes, depending on the drain width and drain depth. Spacing of gratings are determined by the drain depth (at 6m or 18m). | 1000mm x 850mm & 750mm x 850mm | All footpaths within public street | Footpath (gratings) | All | Photo Measurement | Footpath | LTA | Standard Details of Road Elements |  | LTA/SDRE14/4/GRA1 Footnote 1
144 | 157 | Gratings without mild steel plate are not to be used on footpath or cycling paths | NA | All footpaths within public street | Footpath (gratings) | All | Photo | Footpath | LTA | Standard Details of Road Elements |  | LTA/SDRE14/4/GRA1 Footnote 7
145 | 158 | Grating lifting hole to be fully punched through | NA | All footpaths within public street | Footpath (gratings) | All | Photo | Footpath | LTA | Standard Details of Road Elements |  | LTA/SDRE14/4/GRA2
147 | 160 | Headroom clearance for All signages are to be at 2.4m | 2.4m | All cycling and shared path within public street | Cycling/Shared Path | All | Photo Measurement | Cycling Path/ Shared Path | LTA | Standard Details of Road Elements |  | LTA/SDRE17/21/CYC10 Footnote 2
148 | 161 | For a secondary containment facility exposed to the weather, it should be provided with a system to discharge rainwater collected in the facility. The discharge system should be designed and operated to allow only rainwater to be discharged. | Per code requirements | Aboveground Chemical/Fuel Storage Tank | Rainwater discharge system for secondary containment facility exposed to the weather | All | Photo of Additional Evidence | To show the rainwater discharge system provided for secondary containment facility exposed to the weather | NEA | CODE OF PRACTICE FOR POLLUTION CONTROL | Industrial | 11.2.4
149 | 162 | All access routes such as doorways leading to the areas that is within the 5 m setback distance of the cooling towers, should have a clear signage to inform and deter public from entry and accessible only by cooling tower maintenance staffs who understand the risk of Legionellosis and will work in accordance to their safe work procedures based on their risk assessment done. | Per code requirements | All Applicable Areas | Cooling Tower Access Routes | All | Photo of Additional Evidence | To show photos of warning signages and locks provided for all access doorwars leading to areas that are within 5m setback distance of the cooling towers. | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 4.2 (d)
150 | 163 | The fumes from the kitchen exhaust system shall be exhausted above the roof and not face in the direction of adjacent buildings. Where it is not practical to exhaust the fumes at or above the roof, an alternate location of the discharge point in the outdoors may be selected, and not face in the direction of adjacent buildings | Per code requirements | All Applicable Areas | Kitchen Exhaust Outlets | All | Photo of Additional Evidence | To show photos of all the kitchen exhaust outlet locations including the surroundings, and also indicate the total number of kitchen exhaust outlets provided and distance to the nearest neighbouring premise it is facing | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 3.2 (a)
151 | 164 | Trade and industrial premises which carry out activities that can generate air impurities are required to install, operate and maintain air pollution control equipment properly and efficiently. The pollution control equipment has to be designed to comply with the allowable emission standards. | Per code requirements | All Applicable Areas | Pollution Control Equipment | All | Photo of Additional Evidence | To show photo of the installed air pollution control equipment | NEA | CODE OF PRACTICE FOR POLLUTION CONTROL | Industrial | 12.2
152 | 165 | Industries which generate trade effluent that do not meet the allowable limits for discharge into watercourse as specified in Environmental Protection and Management (Trade Effluent) Regulations should install, operate and maintain a treatment plant to treat the effluent to comply with the allowable limits. | Per code requirements | All Applicable Areas | Pollution Control Equipment | All | Photo of Additional Evidence | To show photo of the installed treatment plant to treat trade effluent discharge | NEA | CODE OF PRACTICE FOR POLLUTION CONTROL | Industrial | 11.2.1
153 | 166 | A swimming pool system consisting of pumps, piping, perimeter overflow system, strainer(s), balancing/surge tank, return inlets, filters, automated chemical feeder and other necessary equipment shall be provided for complete circulation of the water through all parts of the pool. | Per code requirements | Swimming Pool | Balancing Tank, Automatic Water Treatment System | All | Photo of Additional Evidence | To show all automatic water treatment systems provided for the swimming pool | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Non-Industrial | 5.2.1.1 (a)
154 | 167 | The design of planting strips(s) close to the edge of AF shall incorporate measures to ensure no overflow of water or run-off from the planting strip(s)/ area(s) into the water. A space of at least 1 m along the perimeter of AF shall be buffered to facilitate maintenance. | Per code requirements | Aquatic Facilities | Planting Strips/ Areas | All | Photo of Measurement | To show photos of measured 1m buffer distances between planting strips(s) along perimeter of AF | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Non-Industrial | 5.2.1 (b)
155 | 168 | The capacity of the containment facility should not be less than the capacity of the largest tank. | Per code requirements | Chemical/Fuel Storage Tank | Containment Facility | All | Photo of Additional Evidence | To show picture of containment facility provided for the chemical/oil store | NEA | CODE OF PRACTICE FOR POLLUTION CONTROL | Industrial | 11.2.4
156 | 169 | The connection point for a filling pipe of a bulk storage tank should be provided with measures to contain spillage. | Per code requirements | Chemical/Fuel Storage Tank | Containment Facility | All | Photo of Additional Evidence | To show measures provided to contain spillage for connection point for a filling pipe of a bulk storage tank | NEA | CODE OF PRACTICE FOR POLLUTION CONTROL | Industrial | 11.2.4
157 | 170 | Chemical/oil store should not have any outlet/opening leading to a storm water drain or a public sewer. | Per code requirements | Chemical/oil store | Containment Facility | All | Photo of Additional Evidence | To show photo of containment facility provided for the chemical/oil store | NEA | CODE OF PRACTICE FOR POLLUTION CONTROL | Industrial | 11.2.5
158 | 171 | Companies which store large quantities of hazardous substances, i.e. at any one time in excess of 100MT in total quantity or 20 MT of IMDG Class 6 (Toxic) hazardous substances in total quantity should provide a retention basin for contaminated fire-fighting water. | Per code requirements | Chemical/oil store | Retention Basin for contaminated fire-fighting water | All | Photo of Additional Evidence | To show the retention basin provided for contaminated fire-fighting water | NEA | CODE OF PRACTICE FOR POLLUTION CONTROL | Industrial | 11.2.5
159 | 172 | The cooling tower shall also be located at least 5 m from any kitchen exhaust discharge outlet, air handling system or other areas where nutrients conveyed from these systems could assist in the growth of Legionella bacteria in the cooling tower system. | Per code requirements | Cooling Towers | Setback Distance | All | Photo of Measurement | To show photo of measured 5m setback distance between cooling tower and kitchen exhaust discharge outlet or similar system. | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 4.2 (b)
160 | 173 | Grease trap shall be installed and sited at suitable location that allows for easy access to facilitate maintenance, not give rise to public health, noise and hygiene problems during operation and maintenance, and be accessible for the transfer of greasy waste directly into Class C waste collection trucks without double transfers. | Per code requirements | Location of Grease Trap | Grease Trap | All | Photo of Additional Evidence | To show the location of the grease trap and the greasy waste collection parking location | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Non-Industrial | 1.9 (a)
161 | 174 | Space allocated for on-site food waste treatment system. | Per code requirements | On-Site Food Waste Treatment System | Food Waste Treatment Room and Equipment | All | Photo of Additional Evidence | To show the space allocation for housing the food waste treatment system | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Commercial, Industrial | 1.10 P1 P2 P3 P4
162 | 175 | If a bin lifter system is employed, there shall be sufficient height clearance to enable the bin lifter to handle the bin properly. | Per code requirements | On-Site Food Waste Treatment System | Food Waste Treatment Room and Equipment | All | Photo of Additional Evidence | To show photo of the bin lifter provided at its highest position in the food waste treatment room | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Commercial, Industrial | 1.10 (b)(ii)
163 | 176 | Provisions shall be made for the effluent (if any) from the food waste treatment system to be discharged into the sewer through a grease trap. | Per code requirements | On-Site Food Waste Treatment System | Food Waste Treatment Room and Equipment | All | Photo of Additional Evidence | To show photo of the grease trap provided for food waste treatment system with clear connection into sewer | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Commercial, Industrial | 1.10 (d)
164 | 177 | The room shall be adequately ventilated and rendered pest proof against birds, rodents and insects. | Per code requirements | On-Site Food Waste Treatment System | Food Waste Treatment Room and Equipment | All | Photo of Additional Evidence | To show pest-proofing provisions for the food waste treatment room | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Commercial, Industrial | 1.10 (e)(ii)
165 | 178 | Additional space for a washing point to wash refuse bins. | Per code requirements | On-Site Food Waste Treatment System | Food Waste Treatment Room and Equipment | All | Photo of Additional Evidence | To show the space allocation for washing of refuse bins in the food waste treatment room | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Commercial, Industrial | 1.10 (e)(iv)
166 | 179 | The entrance and ventilation openings/exhaust discharge shall face away and be aesthetically screened from any neighbouring premises in the vicinity. | Per code requirements | On-Site Food Waste Treatment System | Food Waste Treatment Room and Equipment | All | Photo of Additional Evidence | To show the photo of the entrance and ventilation openings in the food waste treatment room, including the surroundings | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Commercial, Industrial | 1.10 (e)(v)
167 | 180 | Photos of the air intake and discharge valves to be provided showing the level and heat sensors as well as connection to gully trap with strainer. | Per code requirements | Pneumatic Waste Conveyance System (PWCS) | Discharge Valve (DV) Room | All | Photo of Additional Evidence | To show photos of the air intake and discharge valses provided with level sensors and heat sensors. To also show photo of connection of the air intake and discharge valves to the gully trap with strainer. | NEA | SS 642: Code of Practice for Pneumatic Waste Conveyance System | All
168 | 181 | The refuse storage capacity in the PWCS bin centre shall be sufficient for storage of at least two (2) days of refuse output of the development. | Per code requirements | Pneumatic Waste Conveyance System (PWCS) | Refuse compactor | All | Photo of Additional Evidence | To show photo of the PWCS compactor provided (computations to be provided in building plan submissions) | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.7
169 | 182 | The exhaust air discharge point shall also be located at the highest level possible and pointed away from residential dwelling units and commercial spaces within and surrounding the development. | Per code requirements | Pneumatic Waste Conveyance System (PWCS) | Ventilation System | All | Photo of Additional Evidence | To show the photo of the exhaust air discharge point of PWCS, including the surroundings | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.7
170 | 183 | A signage shall be provided above the recyclables chute hopper to inform users of suitable recyclables to be disposed into the chute. | Per code requirements | Recyclables Chute System | Chute Hoppers | All | Photo of Additional Evidence | To show the educational signage above recyclables chute hopper | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Residential | 6.4 (a)
171 | 184 | Clear segregation of refuse and recyclables so as to avoid possible mixing of refuse/recyclables, e.g. with proper partitioning shall be provided to separate the recyclables chute chamber from the refuse chute chamber to minimise contamination of recyclables collected. | Per code requirements | Recyclables Chute System | Recyclables Chute Chamber | All | Photo of Additional Evidence | To show photo of the partitioning wall segregating refuse chute chamber and recyclable chute chamber | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Residential | 6.4 (b)
172 | 185 | A recyclables collection room shall be built at the bottom of a centralised recyclables chute to house a large container. Recyclables collected in the container are transferred to the recyclables collection vehicle. The recyclables collection room shall comply with the same requirements as those for refuses room stated in Section 1.5 and a minimum capacity to accommodate two (2) days of recyclables output. | Per code requirements | Recyclables Chute System | Recyclables Chute Chamber | All | Photo of Additional Evidence | To show all the recyclables bin provided in the recyclables collection point (computations to be provided in building plan submissions) | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Residential | 6.4 (c)
173 | 186 | A pneumatic recyclables chute conveyance system shall comply with the same requirements that apply to pneumatic waste conveyance systems stated in Section 1.7. The capacity of the pneumatic recyclables chute conveyance system shall be sufficient for a minimum of two (2) days of recyclables output. | Per code requirements | Recyclables Chute System | Recyclables Chute System | All | Photo of Additional Evidence | To show picture of the recyclables compactor provided (computations to be provided in building plan submissions) | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Residential | 6.4 (d)
174 | 187 | The daily recyclables output shall be computed to be either an additional 30 % by volume of the daily refuse output estimated under Section 1.2 or 240 L/d of recyclables, whichever is higher. | Per code requirements | Recyclables Collection Point | Recyclables bins | All | Photo of Additional Evidence | Computation to be provided separately in building plan submission | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Residential | 6.2 (b)
175 | 188 | The required roller shutter opening of the bin centre shall be 4m (clear width) by 5m (clear height). | Per code requirements | Refuse Bin Centre | Door | All | Photo of Measurement | To show photo of roller shutter opening at bin centre with measurements indicated | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.6 (j)(i)
176 | 189 | A 5m clear height shall also be provided in front of the entrance when a RORO compactor/container or any other refuse storage system that requires haulage is provided. | Per code requirements | Refuse Bin Centre | Door | All | Photo of Measurement | To show photo measurement of height of roller shutter door at bin centre | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.6 (j)(ii)
177 | 190 | Floor markings shall be provided in front of the entrance of the bin centre to guide the refuse collection vehicle when reversing during operation. | Per code requirements | Refuse Bin Centre | Floor | All | Photo of Additional Evidence | To show the floor markings provided in front of the bin centre to guide the reversing of the refuse collection vehicle | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.6 (j)(ix)
178 | 191 | The bin centre shall be adequately ventilated and rendered pest-proof against birds, rodents and insects. | Per code requirements | Refuse Bin Centre | Pest-proofing | All | Photo of Additional Evidence | To show the pest-proofing provisions for the bin centre | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.6 (f)
179 | 192 | An access walkway of at least 1m clear width around all items in the bin centre shall be provided. | Per code requirements | Refuse Bin Centre | Refuse bins | All | Photo of Measurement | To show photo measurement of width of all access walkway in the bin centre | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.6 (h)
180 | 193 | Where the daily refuse output of the premises is 4,000 litres or more, an enclosed roll-on roll-off (RORO) compactor/container, dust screw compactor or a rotary drum system shall be provided. | Per code requirements | Refuse Bin Centre | Refuse compactor | All | Photo of Additional Evidence | To show the type of compactor installed in the bin centre | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.6 (j)P1
181 | 194 | When there are more than 1 RORO compactor/container in the bin centre, the minimum separation between the adjacent compactor/containers shall be 0.5m. | Per code requirements | Refuse Bin Centre | Refuse compactor | All | Photo of Measurement | To show photo measurement of separation distance between multiple RORO compactors/containers in the bin centre | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.6 (j)(vii)
182 | 195 | The bin centre’s entrance and ventilation openings shall face away from any residential premises in the vicinity. Aesthetic screening shall be provided where practical, so as not to cause a nuisance to neighbouring premises. | Per code requirements | Refuse Bin Centre | Ventilation System | All | Photo of Additional Evidence | To show photo of the refuse bin centre's entrance and ventilation openings, including the surroundings | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.6 (g)
183 | 196 | The bin centre’s floor shall be graded towards a gully/floor-trap connected to the sewer. | Per code requirements | Refuse Bin Centre | Water tap and gully trap with strainer | All | Photo of Additional Evidence | To show photo of the water tap and gully trap with strainer in the refuse bin centre | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.6 (d)
184 | 197 | Where a bin point is provided, washing points and water taps are not required and the bin point need not be connected to the sewer. The bin point shall have a pleasant architectural appearance and be sited so as not to cause a nuisance to neighbouring premises. | Per code requirements | Refuse Bin Point | Water tap | All | Photo of Additional Evidence | To show photo of the bin point provided | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.6 P2
185 | 198 | For developments adopting the Refuse Chute Chamber system, the combined refuse storage capacity of the bin centre or bin point and the refuse chute chambers shall be sufficient for at least two (2) days of refuse output of the development. | Per code requirements | Refuse Bin Point and Refuse Bin Centre | Refuse bins and compactor | All | Photo of Additional Evidence | To show photos of all refuse bins provided at the bin centre, bin point and the refuse chute chamber (if any) | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.6 P1 P2
186 | 199 | An airtight non-corrosive flap door shall be provided for access to the refuse chute chamber. | Per code requirements | Refuse Chute Chamber | Door | 1 | Photo of Additional Evidence | To show photo of the refuse chute chamber door | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Non-Industrial | 1.4 (e)
187 | 200 | The chamber shall be designed to house a SS EN-840 standard wheeled refuse bin which can contain at least one (1) day of refuse output from all the premises connected to the chute | Per code requirements | Refuse Chute Chamber | Refuse bin | All | Photo of Additional Evidence | To show the type of refuse bin used (computation to be provided separately in building plan submission) | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Non-Industrial | 1.4 (a)
188 | 201 | The maximum gap between the termination point of the refuse chute and the top of the bulk bin (with lid open) shall be 200 mm. | Per code requirements | Refuse Chute Chamber | Refuse chute and refuse bin | 1 | Photo of Measurement | To show photo measurement of gap between refuse chute termination point and top of bulk bin provided in the refuse chute chamber | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Non-Industrial | 1.4 (d)
189 | 202 | The refuse room shall be provided with a roller shutter door with a clear width of 3.4m and clear height of 4m. | Per code requirements | Refuse Room | Door | All | Photo of Measurement | To show photo of roller shutter door of refuse room with measurements indicated | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.5 (g)
190 | 203 | The refuse room’s floor shall be graded towards a gully/floor trap connected to the sewer. | Per code requirements | Refuse Room | Gully trap with strainer | 1 | Photo of Additional Evidence | To show photo of gully trap/floor trap with strainer connected to sewer in refuse room | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.5 (d)
191 | 204 | The refuse room shall be rendered pest-proof against birds, rodents and insects. | Per code requirements | Refuse Room | Pest-proofing | All | Photo of Additional Evidence | To show the pest proof netting for openings of the refuse room | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.5 (f)
192 | 205 | The vehicular service road to the refuse room shall be free from obstruction and such that the refuse collection vehicle can make a three-point turn within the premises to back up into the refuse room. | Per code requirements | Refuse Room | Refuse collection truck | All | Video Recording | Video Recording of refuse collection truck making a three-point turn and backing up into the refuse room. | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.5 (b)
193 | 206 | A setback distance of at least 13 m shall be provided to ensure that the bin centre is accessible to refuse collection vehicles. The swept path of a refuse truck from the main or service road to the bin centre shall meet the minimum required turning radius of 9m and also be free of obstructions. | Per code requirements | Refuse Room | Refuse collection truck | All | Video Recording | Video Recording showing the ingress/ egress of the refuse truck from the entrance of the development to the bin centre | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.6 (j)(iii)
194 | 207 | The refuse room shall house a mechanical refuse handling equipment, e.g. a dust-screw or any other enclosed fixed system. Refuse collected in the refuse handling equipment is conveyed directly into a refuse collection vehicle, which backs up into the refuse room. | Per code requirements | Refuse Room | Refuse handling equipment | All | Photo of Additional Evidence | To show the type of refuse handing equipment installed in the refuse room | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.5 P1
195 | 208 | A water tap shall be provided | Per code requirements | Refuse Room | Water tap | 1 | Photo of Additional Evidence | To show the that the water tap has been installed in the refuse room | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.5 (e)
196 | 209 | The chute shall terminate at the roof of a building. The chute shall be ventilated at the top with at least two openings of effective area not less than 0.1 sq m each. This top section of the refuse chute shall be accessible from the common area to facilitate maintenance. | Per code requirements | Roof | Chute ventilation openings on roof | All | Photo of Measurement | To show photo of refuse chute ventilation opening at the roof, with measurements indicated. | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Non-Industrial | 1.3 (b)
197 | 210 | If the roof is to be used as a roof terrace/garden, particular attention shall be paid to the siting of the refuse chute, the location of its openings and the maintenance requirements so as not to cause any smell nuisance. Ventilation openings shall be located at least 2.1 m above roof level. | Per code requirements | Roof terrace/ garden | Chute ventilation openings on roof | All | Photo of Measurement | To show photo measurement of the vertical distance between refuse chute ventilation opening and roof terrace/garden level | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Non-Industrial | 1.3 (c)
198 | 211 | With effect from 1 November 2005, no roof gutters should be installed for any new developments. | Per code requirements | Roof | Roof Structures | All | Photo of Additional Evidence | To show photos of all roof structures. Where roof structures include provision of roof gutters, scupper drains, rainwater outlets, rainwater downpipes, to show additional photos of permanent access, and design considerations provided to ensure maintenance can be carried out safely | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 7.2 (a)
199 | 212 | The number of public toilets and sanitary fittings to be provided in buildings accessible to the general public is given in Appendix 2. The numbers of facilities provided are minimum requirements and QPs should design the toilets to ensure sufficient facilities are provided based on the expected toilet use during peak hours. | Per code requirements | Toilet area | Number of Sanitary fittings | All | Photo of Additional Evidence | To show photo of all the sanitary fittings provided for Public Toilets, and also indicate in the scan the total number of sanitary fittings provided | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | Non-Industrial | 2.4.1 (a)
200 | 213 | For a secondary containment facility that is fully enclosed, a leak detection system with an alarm device should be provided within the facility. | Per code requirements | Underground Fuel Storage Tank | leak detection system with an alarm device | All | Photo of Additional Evidence | To show leak detection system with an alarm device provided | NEA | CODE OF PRACTICE FOR POLLUTION CONTROL | Industrial | 11.2.4
201 | 214 | Developments not adopting the Refuse Room system i.e. those with or without refuse chambers shall be provided with either a bin point or a bin centre within the premises. A bin centre shall be provided if refuse output exceeds 1,000 litres/day. The bin centre or bin point capacity shall be sufficient for at least two (2) days of refuse output of the development. | Per code requirements | Refuse Bin point and Refuse Bin Centre | Refuse bins | All | Photo of Additional Evidence | To show photos of all the refuse bins provided at the refuse bin point or bin centre. | NEA | CODE OF PRACTICE ON ENVIRONMENTAL HEALTH | All | 1.6 P1 P2
202 | 215 | Retention of trees, plants and vegetation approved for conservation (Internal Works) | As per approved Plans | All Applicable Areas | trees, plants and vegetation | All | Photos | Photos of individual conserved trees and plants (Internal Works) | NParks | Guidelines on greenery provision and tree conservation for developments | All
203 | 216 | Planting scheme comply with approved plan | As per approved Plans | All Planting Areas | Trees, Hedges, Shrubs, Turf | All | Photos | Photos of individual proposed trees, overview photos of proposed hedges, shrubs and turf (Internal Works) | NParks | Guidelines on greenery provision and tree conservation for developments | All
204 | 217 | Provision of planting areas, i.e. green buffer, peripheral planting verge and planting area at open air parking area (street level) | As per approved Plans | All Planting Areas | Planting Areas | All | Photos | Overview photos of planting areas (Internal Works) | NParks | Guidelines on greenery provision and tree conservation for developments | All
205 | 218 | Retention of trees, plants and vegetation approved for conservation (External Works) | As per approved Plans | All Applicable Areas | trees, plants and vegetation | All | Photos | Photos of individual conserved trees and plants (External Works) | NParks | Guidelines on greenery provision and tree conservation for developments | All
206 | 219 | Planting scheme of roadside green verges | As per approved Plans | Roadside Green Verges | Trees, Hedges, Shrubs, Turf | All | Photos | Photos of individual proposed trees, overview photos of proposed hedges, shrubs and turf (External Works) | NParks | Guidelines on greenery provision and tree conservation for developments | All
207 | 220 | Provision and reinstatement of green verges and areas under NParks management | As per approved Plans | All Applicable Areas | Green Verges | All | Photos | Overview photos of green verges (External Works) | NParks | Guidelines on greenery provision and tree conservation for developments | All
208 | 221 | [Sewerage Works] Conduct visual checks on the manhole's interior to ensure they are constructed as per approved drawings and in accordance with PUB's COP. Manholes/Chambers/Shafts checks include presence of manhole netting, sign of water seepage, presence of HDPE lining, intermediate platform orientation, bending radius of benching, brickwork height [between 120 ~ 450mm], Distance between the MH chamber wall to the channel [min. 400mm], Height difference between the manhole top slab to the intermediate platform [between 2400mm~4800mm], etc.) | Verify against submitted as-built plans | All Applicable Areas | Manholes | All manholes | Photo of Additional Evidence |  | PUB | Code pf Practice on Sewerage and Sanitary Works | All | 3
209 | 222 | Compliance to QP Submitted As-Built Drawings of the sanitary drainage system (e.g. branch /main drain-lines check include diameter, length, pipe materials, connections. Inspection chamber checks include type of cover, thickness of cover slab, location etc.) | Per code requirements (COPSSW) | All Applicable Areas | Sanitary System Design | All | Photo of Additional Evidence |  | PUB | Code pf Practice on Sewerage and Sanitary Works | All | 4
210 | 223 | Compliance to QP Submitted As-Built Drawings of the sanitary plumbing system (e.g. check on floor trap include provision of anti-mosquito device, min water seal of 50mm, location of waste pipe, type of covers, location of floor trap and its connection to waste appliances etc. Check on discharge stack include provision of cleaning eye, vent cowl at the top, termination height above the roof etc. Type of venting to be provided for different configuration os urinals/ basins, installation location of vacuum breaker flush valve etc.) | Per code requirements (COPSSW) | All Applicable Areas | Sanitary System Design | All | Photo of Additional Evidence |  | PUB | Code pf Practice on Sewerage and Sanitary Works | All | 4
211 | 224 | Compliance to QP Submitted As-Built Drawings of the sanitary appliances (e.g. check include provision of kerb at wash area, location, pipe connection from kitchen to grease trap, fittings in grease traps (i.e. brickwall, screen bar, strainer bucket etc.), | Per code requirements (COPSSW) | All Applicable Areas | Sanitary System Design | All | Photo of Additional Evidence |  | PUB | Code pf Practice on Sewerage and Sanitary Works | All | 4
212 | 225 | Compliance to QP Submitted As-Built Drawings of the sanitary pump system (e.g. Pump, Pipework & Fittings, Electrical Panels) | Per code requirements (COPSSW) | Basement equipment room/chamber | Sanitary Pump Equipment | All affected areas | Photo of Additional Evidence |  | PUB | Code pf Practice on Sewerage and Sanitary Works | All | 3.3
213 | 226 | A.3) Access with removable cover shall be provided at the junctions/bends/fittings of pipe/stack. | Per code requirements | Residential Units |  |  | Photo of Additional Evidence | Require to show all the pipe connection without removable cover i.e. removable cover should be removed before taking the pictures. | PUB |  | Residential
214 | 227 | B.1) Floor Trap/ Gully Trap: Approved anti-mosquito device should be provided for all the floor traps. | Per code requirements | Residential Units |  |  | Photo of Additional Evidence | Require contractor to take a zoom in photo to show the internal condition of the anti-mosquito device | PUB |  | Residential
215 | 228 | B.6) Floor Trap/ Gully Trap: Waste pipe should not protrude into the riser of the trap | Per code requirements | Residential Units |  |  | Photo of Additional Evidence | Require contractor to take a zoom in photo to show floor trap top view without the anti-mosquito device | PUB |  | Residential
216 | 229 | B.8) Floor Trap/ Gully Trap: Double 45 degree bends are to be incorporated between the floor trap and the wc for 'P' trap and pan connected in series to the same discharge pipe. | Per code requirements |  |  |  | Photo of Additional Evidence | For basement high level unit with toilet connected above. 360 footage to show overview of the discharge pipe connection stated above | PUB |  | All
217 | 230 | B.9) Floor Trap/ Gully Trap: A floor trap shall be provided to receive connection from waste appliances (Wash basins etc.) before discharging into the branch drain-line. The trap shall have a minimum water seal of 50mm. Wash basins connect to floor trap(FT). | Per code requirements |  |  |  | Photo of Additional Evidence | This is for floor trap at ground level e.g. childcare / wash area. For basement high level unit with wash basin connected above. 360 footage to show overview of the waste pipe connection stated above | PUB |  | All
218 | 231 | Size of the drains shall be built according to the approved construction draings | -50 | All | Drains | All | Photo of Measurement |  | PUB | Approved Document | All
219 | 232 | Drains shall be unobstructed by debris, construction materials or any unauthorised material |  | All | Drains | All | Photo of Additional Evidence |  | PUB | Approved Document | All
220 | 233 | Drains shall be handed over with no visual structural defects (i.e cracks, honeycomb, exposed rebar, formworks) |  | All | Drains | All | Video Recording |  | PUB | Approved Document | All
221 | 234 | Safety Railings shall be installed next to open drains (>1m depth). Type and measurements to be in accordance with the COP. | -50 | All | Railings | All | Photo of Measurement |  | PUB | Code of Practise for Stormwater Drainage | All | 9.9
222 | 235 | Drop-inlet chambers and concealed scupper drainage shall be designed in accordance with the Land Transport Authority's latest Standard Details of Road Elements and shall be provided at maximum 6 m spacings along all road carriageways. | <6000 | All | Drop Inlet Chamber & Concealed Scupper Pipes | All | Photo of Measurement |  | PUB | Code of Practise for Stormwater Drainage | All | 9.8.1
223 | 236 | Concealed Scupper Drainage pipe is continuous, free from silt or debris and flushed with drain wall. Intermediate sump required if DIC and RSD >6m |  | All | Concealed Scupper Pipes | All | Photo of Additional Evidence |  | PUB | Code of Practise for Stormwater Drainage | All | 9.8
224 | 237 | Non skid aluminium rungs shall be provided at every opening/grating for closed drains with internal depth equal to or greater than 0.9m | >900 | All | Rungs | All | Photo of Measurement |  | PUB | Code of Practise for Stormwater Drainage | All | 9.1
225 | 238 | where the entrance culvert/crossing is shallower than 600 mm, hinged open gratings shall be installed throughout the whole length of the entrance culvert/crossing | <600 | All | Gratings | All | Photo of Additional Evidence |  | PUB | Code of Practise for Stormwater Drainage | All | 9.12.2
264 | 239 | Dimension / Size - Size of external drains (e.g. drop-inlet chambers, roadside drains, entrance culvert, common drain) are in accordance of approved plans and as-built plans submitted. For drains, photographs of measurements are to be taken at 3 points per section with different cross-section - upstream end, downstream end and mid-point. | -50 | All | Drains | All | Dimensional evidence |  | PUB | Approved Document | All
265 | 240 | Free-Flowing / Unobstructed - External drains (e.g. drop-inlet chambers, roadside drains, entrance culvert, common drain) shall be unobstructed by debris, construction materials or any unauthorised material. |  | All | Drains | All | Video recording evidence |  | PUB | Approved Document | All
266 | 241 | Structural Condition - External drains (e.g. drop-inlet chambers, roadside drains, entrance culvert, common drain) shall be handed over with no visual structural defects (i.e cracks, honeycomb, exposed rebar, formworks) |  | All | Drains | All | Video recording evidence |  | PUB | Approved Document | All
267 | 242 | Safety Railings shall be installed next to open external drains (>1m depth). Type and measurements to be in accordance with the COP. Photographs of measurements showing distance of base of safety railing to drain invert are to be taken from lowest point, mid point and highest point at the section to be handed over. | -50 | All | Railings | All | Dimensional evidence |  | PUB | Code of Practise for Stormwater Drainage | All | 9.9
268 | 243 | Drop-inlet chambers (DICs) and concealed scupper drainage shall be designed in accordance with LTA's latest Standard Details of Road Elements and shall be provided at maximum 6m spacings along all road carriageways. Photographs of measurements showing spacing are to be taken for all DICs / concealed scupper drainage. | <6000 | All | Drop Inlet Chamber & Concealed Scupper Pipes | All | Dimensional evidence |  | PUB | Code of Practise for Stormwater Drainage | All | 9.8.1
269 | 244 | Concealed Scupper Drainage pipe is continuous, free from silt or debris and flushed with drain wall. Intermediate sump required if DIC and RSD >6m. Photographs of measurement of scupper to drain wall shall be provided. If >6m, photo of intermediate sump to be provided. |  | All | Concealed Scupper Pipes | All | Dimensional evidence |  | PUB | Code of Practise for Stormwater Drainage | All | 9.8
270 | 245 | Non skid aluminium rungs shall be provided at every opening/grating for closed external drains with internal depth equal to or greater than 0.9m Photographs of measurement for closed external drains <0.9m at opening/grating to be provided if there are no rungs provided. Photographs of rungs provided at opening/grating if otherwise >0.9m. | >900 | All | Rungs | All | Dimensional evidence and closed up photo evidence |  | PUB | Code of Practise for Stormwater Drainage | All | 9.1
271 | 246 | For entrance culvert/crossing shallower than 600 mm, hinged open gratings shall be installed throughout the whole length of the entrance culvert/crossing Photos of measurement for entrance culvert/crossing <600mm and photos of hinge open gratings to be provided. | <600 | All | Gratings | All | Dimensional evidence and closed up photo evidence |  | PUB | Code of Practise for Stormwater Drainage | All | 9.12.2
226 | 247 | Access openings not less than 850mm wide by 1000mm high with sill height of not more than 1100mm and head height not less than 1800mm above the inside floor level. | size of opening>=850mm by 1000mm, sill <=1100mm from finished floor, head height >=1800mm | All Applicable Areas | Access opening | 1 | Photo of Measurement | Photo to show size of access opening (Width and height) and also the sill and head height for inside floor level | SCDF | Fire Code | All
227 | 248 | Fire doors are with certification body’s labels. | Fire rating and serial number | All Applicable Areas | Fire rated doors (Labels) | 2 | Photo of Additional Evidence | To show close up of the label and indicate the total number of Fire-rated doors on this floor | SCDF | Fire Code | All
228 | 249 | MAP/SAP of certification body’s listed type and be in bright red colour. | Serial number | All Applicable Areas | Main Alarm Panel And Sub- Alarm Panel (Labels) | 1 | Photo of Additional Evidence | To show close up of the label | SCDF | SS 645 | All
229 | 250 | Fire dampers with certification body’s labels and approved fire rating are provided. | Serial number | All Applicable Areas | Mechanical Ventilation/ Air-Conditioning System - Label | 2 | Photo of Additional Evidence | To show close up of the label and indicate the total number of Fire-rated doors on this floor | SCDF | Fire Code | All
230 | 251 | Double layered protection provided where false ceiling depth exceeds 400mm/800mm (tenancy/common areas respectively). | Secondary detector layer | All Applicable Areas | Smoke/Heat Detector - Concealed Ceiling | 1 | Photo of Additional Evidence | To show the double layered protection | SCDF | SS 645 | All
231 | 252 | Protection provided to raised floor whose depth exceeds 400mm. | Raised floor depth | All Applicable Areas | Smoke/Heat Detector - Raised floor | 1 | Photo of Additional Evidence | To show the protection | SCDF | SS 645 | All
232 | 253 | Double layer provided for ceiling void more than 400mm (tenancy)/800mm (non-tenancy). | Secondary sprinkler layer | All Applicable Areas | Sprinkler System | 1 | Photo of Additional Evidence | To show the double layered protection | SCDF | Fire Code | All
233 | 254 | Under-duct sprinkler provided for MV ducting (either in single or in combination) with width more than 800mm/1000mm/1200mm. | Under-duct sprinkler | All Applicable Areas | Sprinkler System | 1 | Photo of Additional Evidence | To show the system that is in the under-duct | SCDF | Fire Code | All
234 | 255 | Break tank of minimum size 11.5 m3 provided. | >=11.5m3 | Break Tank / Intermediate Tank And Transfer Pump | Break tank volume | 1 | Photo of Additional Evidence | To show the printing of tank serving what fire protection system and volume | SCDF | Fire Code | All
235 | 256 | Intake and discharge locations with at least 5 metres separation. | >=5m | Carpark | Basement Carpark Mechanical Ventilation/Smoke Extraction System | 1 | Photo of Measurement |  | SCDF | Fire Code | All
236 | 257 | Minimum clear width of exit door is more than 850 mm. | >=850mm | Common area | Exit door | 2 | Photo of Measurement |  | SCDF | Fire Code | All
237 | 258 | Exit signs are installed between 2.2m and 2.5m height from floor level above exit doors. | 2.2m to 2.5m | Common area | Exit sign | 2 | Photo of Measurement |  | SCDF | Fire Code | All
238 | 259 | [FE] Fire extinguisher installation height is about 1m from floor level. | 1m | Common area | Fire extinguisher | 1 | Photo of Measurement |  | SCDF | Fire Code | All
239 | 260 | Certification body’s labels are provided for all exit sign. | Serial number | Common area | Label | 2 | Photo of Additional Evidence | To show the close up of the label | SCDF | Fire Code | All
240 | 261 | Certification body’s labels are provided for all emergency lighting. | Serial number | Common area | Label | 2 | Photo of Additional Evidence | To show the close up of the label | SCDF | Fire Code | All
241 | 262 | [DR&WR] Landing valve 760mm to 1 meter above finished floor level. | 760mm to 1m | Common area | Landing valve | 1 | Photo of Measurement | Measurement from lowest point of landing valve to floor level | SCDF | Fire Code | All
242 | 263 | Height of manual call point is 1.4m from floor level | 1.4m | Common area | Manual call point | 1 | Photo of Measurement |  | SCDF | Fire Code | All
243 | 264 | Escape corridor/passageway width more than 1200mm. | >=1200mm | Common area | Narrowest part of corridor | 2 | Photo of Measurement | To show 2 different area with one of the sample photo to be the narrowest measurement | SCDF | Fire Code | All
244 | 265 | Distress button or voice communication located between 800mm and 1200mm above ground level. | 800mm to 1200mm | Common area | PWD distress button | 1 | Photo of Measurement |  | SCDF | Fire Code | All
245 | 266 | For PWD holding point designated in an external corridor positioned at least 2000mm away from the edge of exit staircase. | >=2000mm | Common area | PWD holding point | 1 | Photo of Measurement | Measure distance of PWD holding point from exit staircase | SCDF | Fire Code | All
246 | 267 | For PWD holding point within the fire fighting lobby and smoke stop lobby, positioned at least 500mm away from the edge of exit staircase and away from the occupant escape path. | >=500mm | Common area | PWD holding point | 1 | Photo of Measurement | Measure distance of PWD holding point from exit staircase | SCDF | Fire Code | All
247 | 268 | The space provided for a wheelchair in a PWD Holding Point at least 900mm X 1400mm. | >=900mm by >=1400mm | Common area | PWD holding point | 1 | Photo of Measurement |  | SCDF | Fire Code | All
248 | 269 | The evacuation lift has a clear platform size of minimum 1200mm width X 1400mm depth. | >=1200mm by >=1400mm | Evacuation lift | Evacuation lift car | 1 | Photo of Measurement | Measurement of lift car internal | SCDF | Fire Code | All
249 | 270 | Fire engine access road with a minimum 4m width. | >=4m | External ground storey | Fire engine access road | 2 | Photo of Measurement | To show 2 different area with one of the sample photo to be the narrowest measurement | SCDF | Fire Code | All
250 | 271 | Accessway width 6m provided. | >=6m | External ground storey | Fire engine accessway | 2 | Photo of Measurement | To show 2 different area with one of the sample photo to be the narrowest measurement | SCDF | Fire Code | All
251 | 272 | Overhead clearance of 4.5m provided over access path. | >=4.5m | External ground storey | Overhead obstruction along fire engine access | 1 | Photo of Measurement |  | SCDF | Fire Code | All
252 | 273 | Buildings fitted with rising mains and automatic sprinkler system have accessways for pumping appliances within 18m of the breeching inlet. | <=18m | Ground storey | Breeching inlet from fire engine access | 1 | Photo of Measurement | Measure shortest travelling distance between FEA to BI | SCDF | Fire Code | All
253 | 274 | Certification body’s label provided for system. | Serial number | Kitchen | Kitchen Fire Suppression System (Labels) | 1 | Photo of Additional Evidence | To show the close up of the label | SCDF | Fire Code | All
254 | 275 | Certification body’s label for fire lift provided.. | Serial number | Lift | Lift Door -Label | 1 | Photo of Additional Evidence | To show close up of the label and indicate the total number of Fire-rated doors on this floor | SCDF | Fire Code | All
255 | 276 | Fire door provided with door closer. For protected riser shafts <750mm depth, door closers can be omitted. For protected riser shafts >750mm depth, door closers and door selector for double leaf doors shall be provided. | <750mm | M&E Stack | Riser shaft - Depth of riser | 1 | Photo of Measurement | Measurement of the depth (deepest one) of riser shaft from door | SCDF | Fire Code | All
256 | 277 | 4-way inlet provided (for 150mm diameter riser stack). | 150mm | M&E Stack | Wet Rising Main - Breeching inlet pipe | 1 | Photo of Additional Evidence | Open the glass front and take photo of the breeching inlet | SCDF | SS 575 | All
257 | 278 | There are no unprotected openings within 3m horizontally and 3m vertically from any part of external exit staircase. | >=3m horizontally, >=3m vertically | Staircase Area | External Exit Staircase (Unprotected openings) | 1 per staircase | Photo of Measurement | Measurement of shortest distance between external exit staircase from any unprotected opening / space | SCDF | Fire Code | All
258 | 279 | There are no unprotected openings within 1.5m horizontally and 3m vertically below any opening in the external wall of the internal exit staircase. | >=1.5m horizontally, >=3m vertically | Staircase Area | Internal Exit Staircase (Unprotected openings) | 1 per staircase | Photo of Measurement | Measurement of shortest distance (>=1.5m horizontally, >=3m vertically) between internal exit staircase from any unprotected opening / space | SCDF | Fire Code | All
259 | 280 | All exit staircases discharge at ground level directly into a safe exterior space opened to the sky. (For sprinkler protected buildings, a maximum 50% of the total number of exit staircase is allowed to be discharged to covered circulation space.) | Open to sky / external | Staircase Area | Staircase discharge | 1 per staircase | Photo of Additional Evidence | Measurement of longest distance from exit staircase last step to open to sky space. | SCDF | Fire Code | All
260 | 281 | To provide evidence that the roof/floor slab of the affected area has been demolished. |  | Area proposed for decantment of GFA | - | All affected areas | Photo of Additional Evidence | To provide the past photo of the roof/floor that was removed. | URA | Compliance with Approved plans | All | Applies only for proposals that involve decantment.
261 | 282 | To provide photographic evidence that the integration works for the Common Service Tunnel (CST) have been implemented as approved. This includes photos of the measurements of the structural elements. |  | CST integration area | Structural elements such as the RC wall of the CST Tunnel, RC slab with services | All | Photo of Measurement |  | URA | Common Services Tunnel | Residential | Applies only to Marina Bay which is the gazetted Common Services Tunnel area. To check if defect, cracks, water leakages are visible
262 | 283 | To provide photographic evidence that the softscape and hardscape areas have been implemented as approved. This includes as-built evidence of lush planting based on the approved plant species at the approved landscaped locations. |  | Landscaped Areas | - | Sample of affected areas | Photo of Additional Evidence | Applies only to New Erection Proposals within strategic areas. To double check if landscaping is visible from 360 Capture already and whether additional photo evidence required. | URA | Landscape Replacement Area guidelines Compliance with approved plans | Residential
263 | 284 | To provide photographic and video evidence that the all conserved elements are restored and structural components built as per approved plan | As per Conservation Guidelines and Specific Restoration Guidelines | Front, Side, Rear, Roof Key interiors Key structural components and material Key conserved elements | Key external and internal views of the conserved building Aerial roof views including adjacent units | All affected areas | Photo of Additional Evidence Photo of Measurement | To provide description of the photo and video based on the conserved element and structural component | URA | Conservation Guidelines Approved Plan | All

## Dropdown (hidden)
Mode of Evidence | Type of Plan
Photo of Measurement | Typical
Photo of Additional Evidence | Non-Typical
Video Recording |  | Full
Document Attachment |  | Hybrid
NA