## Project Details
Project Description | Please fill
Project Reference Number | Please fill
Project Typology | Please fill
SGFA | Please fill
Occupant load | Please fill
Habitable height | Please fill
Is there PWCS in this project | Please fill
Developer | Please fill
QP | Please fill
Main Con | Please fill

## VI Plan
General Instruction
1. Please complete the Overall Project Details​ and Virtual Inspection Scope​ 2.Please create new rows if there are more Buildings or Virtual Scans Planned 3. If there is no Partial TOP Phases, please indicate "1" for column A
Overall Project Details​
Project Reference Number​ |  |  |  | [Please fill]
Virtual Inspection Vendor ​ |  |  |  | [Please fill]
Building |  | Typical Floors |  | Non-Typical Floors
|  | [Please fill] |  | [Please fill]
Blk 1 |  | 1. Carpark B1 and B2 |  | 1. Roof Level 25
|  | 2. Level 2 to 15 |  | 2. Level 1
3. Level 16 to 24
Blk 2 |  | 1. Carpark B1 and B2 |  | 1. Roof Level 25
|  | 2. Level 2 to 15 |  | 2. Level 1
3. Level 16 to 24
MSCP |  | 1. Floor 1 to 4 |  | 1. Roof Garden Floor 5
Common Area |  | NA |  | 1. Level 1
2. Level 2 E-deck
3. Tennis Court
[Please Add if necessary]
Virtual Inspection Scope​
Partial TOP Phase | Virtual Scan Submission | Proposed Scanned Area ​ | Agencies/Dept Inspection ​ | Expected Date ​ | 360 Capture Link​ | Remarks
Please update when you have made the booking​
1 | Virtual Scan 1 ​ ([Please fill] For Blk 1) | [Please fill] | [Please fill] BCA, SCDF, NEA, PUB​ | [Please fill] |  | The first Virtual Scan can only be submitted after the VI Plan has been cleared by the Consultation Officer
[Typical] ​
Block 1
Floor 4 , Floor 14,​
Floor 16, Floor 20
Carpark B1​
​
[Non-Typical] ​
Block 1
Level 1 and Roof Level 25​
[Please Add if necessary]
| Physical Inspection ​ (if applicable) | Areas that require functional checks/additional checks | BCA Inspection | Please fill |  | Please submit the last Scan 3 days before the 1st Physical Inspection date
|  |  | SCDF Inspection | Please fill
|  |  | PUB Inspection | Please fill
|  |  | NEA Inspection | Please fill
2 | Virtual Scan 1 ([Please fill] For Blk 2 and MSCP) | [Please fill] | Please fill BCA, SCDF, NEA, PUB​ | [Please fill] |  | The first Virtual Scan can only be submitted after the VI Plan has been cleared by the Consultation Officer
[Typical] ​
Block 2​
Floor 5 , Floor 15,​
Floor 16, Floor 24
Carpark B2​
​
[Non-Typical] ​
Block 2
Level 1 and Roof Level 25​
MPCP Floor 3​
| Virtual Scan 2 ([Please fill] Common Area) ​ | [Please fill] | Please fill BCA, SCDF, NEA, PUB​ | Please fill |  | Please submit consecutive scans at least 1 week apart
1. Level 1 ​
2. Level 2 E-deck​
3. Tennis Court​
[Please Add if necessary]
| Physical Inspection ​ (if applicable) | Areas that require functional checks/additional checks | BCA Inspection | Please fill |  | Please submit the last Scan 3 days before the 1st Physical Inspection date
|  |  | SCDF Inspection | Please fill
|  |  | PUB Inspection | Please fill
|  |  | NEA Inspection | Please fill
[Please Add if necessary]

## VI Scans
General Instruction
1. Please provide the Plan view and Section view of the project and colour the areas for each Virtual Scan Submission
Please provide a plan view demarcating the different scans | Please provide the elevation plan with the proposed scanned floors and details(like the different unit layout)
Please provide the planned capture routes

## Target Milestones
Month | Key Milestones | Target Date (to fill) | Remarks
Within 3 Months | Virtual Scan 1 ​ | Please fill | All scanned areas have to be completed and must be in condition that is suitable fo inspection. All submitted virtual scan(s) for SCDF inspection must be accompanied with Qualified Person’s Certificate of Fire Safety Works (CFSW) and Registered Inspector’s Certificate of Inspection (Form 1 or 2). The CFSW and Form 1 or 2 shall be sent together with the link for virtual scan, to the inspection officer via email. QP’s CFSW and RI’s Form shall indicate clearly on the project title with description of the areas that are checked and certified).
| Virtual Scan 2​ | Please fill
| Virtual Scan 3 | Please fill
[Please Add if necessary]
| PUB Submission | Please fill | Inspection date can be arranged in advance (>1 month before). However, documents must be submitted and cleared for the inspection to proceed. Qualified Persons (QPs) / Professional Engineers (PEs) are to make submissions and obtained clearance from PUB for Completion of Sanitary Works.
| Physical Inspection ​ 1 (PUB) | Please fill | Please assume that PUB physical checks are required. As above, the date should be at least 1 month after the PUB application
| NEA Submission | Please fill | List of documents needed to be submitted before the physical inspection: • As-built architectural drawings including site plan • PWCS drawings endorsed by the relevant QP • As-built chute hopper details/ drawings • Testing and commissioning reports for the PWCS
| Physical Inspection ​ 2 (NEA) | Please fill | Please assume that NEA physical checks are required. The date should be at least 1 month after the NEA application
| TFP Application Submission | Please fill
| Zoom Briefing meeting with SCDF | Please fill
| Physical Inspection ​ 3 (SCDF) | Please fill | Please assume that SCDF physical checks are required. The date should be at least 2 weeks after the TFP application
| Physical Inspection ​ 4 (BCA) | Please fill | Please assume that BCA physical checks are required. The date should be at least 7 days after the last Virtual san was submitted QP delcaration must be submitted 3 days before CONQUAS/QM must be completed
| BCA Submission | Please fill
Please complete the targeted dates. Upon review, if physical inspections is not required, the project team would be updated

## Waiver List
S/n | Agency | Description of Waiver Item | Affected Areas | Clause | Decision
Eg. | BCA | To allow adjacent wall to the centre line of water closet to be 400mm. | Unit type A2, A3-P, B3, B3-P & B3-H (Total:169) | Code on Accessibility in the Built Environment 2013 Clause 7.3.5.b | Approved
1